## Slide 1: Mentoring for Change
Setting a new course for the Mentor Program

## Slide 2: Snapshot of the Mentor Program
8 mentors + 4 mentors-in-training
Certification program
Goal: set libraries up to participate in the IDS Project
  We do all of the heavy lifting
  Slapdash implementation
Efforts centered upon new member libraries

## Slide 3: Problems & Pitfalls
One size does not fit all
  Checklist is good on paper…
  But implementation seldom goes that easily
No deadlines, but many delays
  Ideally, 2 visits and we’re done
  But in reality, undiscovered problems cause delays
Experts in superficial changes
  We excel at optimizing systems & workflows
  But we do not optimize staff for lasting change

## Slide 4: Living up to our name
A mentor is a trusted advisor
  Helps mentees develop skills & knowledge
  Trusting relationship with a clear, mutual purpose
Basic principles*
  Form agreement with mentees on goals for relationship
  Be patient – mistakes will happen
  Help mentees succeed on their own terms
  Schedule ongoing contact with mentees
This is fundamentally a teaching relationship
*From Buller, J. "Serving as a Mentor." The Essential College Professor: A Practical Guide to an Academic Career, 348-354.

## Slide 5: Shifting Course
We must approach each library as a student
Together with them, we need to:
  Set expectations, goals, and deadlines
  Develop a plan for implementing change
  Provide support and training
  Communicate regularly
Our goal is to teach libraries to plan, implement, & maintain positive change

## Slide 6: The Nutshell
Goal setting
Together, IDS team & library representatives set goals & sign agreement.
Planning
Mentors review library’s existing workflow & systems.
Execution
Library begins implementation plan.
Together, discuss findings & recommended changes.
Together, create an implementation plan with milestones, tasks, and a deadline.
Library assigns liaisons to work directly with mentors.
Together, meet on a regular schedule to discuss progress.
Mentors provide support & training as needed.
Completion
Together, reflect on accomplishments.
Mentors submit a written report to the library.
Liaisons provide feedback on experience.
Team introduces the mentoring process to the library.

## Slide 7: Playing on our strengths
Workflow Mentors
ILLiad & Customization Manager experts.
Grounded in ILL/DD best practices.
Work with libraries to improve their ILL/DD operations.
Lead the implementation planning process.
Systems Mentors
Library systems experts.
Understand how systems are used within the IDS Project.
Know how to implement & troubleshoot tools developed in the IDS Project.
Help libraries use their systems more effectively.

## Slide 8: Next steps
Now
Create implementation plans w/ current libraries
March
ILLiad Conference
Finalize new mentor process
Implement new mentor process
April
Mentor Certification Program begins
Begin outreach to veteran members
Develop supporting materials & templates
Summer
Review & revise new process
Mentor Certification Program finishes
IDS Project Conference
Distribute supporting materials

## Slide 9: Questions? Comments?
What do you think?